## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Work Product Cross Reference/Details sheet | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | OnlineWallet:001 | Design Documentation for Backend application | Satya | Satya | Average | Low |  | R&D | Non-Functional |  |  |  |  | 18 hrs | Design is fullfilled against business requirement
2 | 2 | Standard document | High | OnlineWallet:002 | Test Plan | Satya | Satya | Average | Low |  | R&D | Non-Functional |  |  |  |  | 8 hrs | Checking whether the test case is fullfiled with user acceptance criteria document
3 | 3 | Standard document | High | OnlineWallet:003 | Bootstrapping the project | Satya | Satya | Simple | Low |  | R&D | Non-Functional |  |  |  |  | 4 hrs | Checking against the application setup and ensuring the required dependencies, running the main code and checking the server is started without errors
4 | 4 | Work session | High | OnlineWallet:004 | Entity Class Design Table Design and Populating the data | Satya Karan | Satya Karan | Complex | Low |  | R&D | Functional |  |  |  |  | 8 hrs | Checking against the table design in RD
5 | 5 | Work session | High | OnlineWallet:005 | Registering user: basic details to be filled by the user | Satya | Satya | Average | Low |  | R&D | Functional |  |  |  |  | 8 hrs | Checking whether the user is registered or not
6 | 6 | Work session | High | OnlineWallet:006 | Logging in: email id and password required | Karan | Karan | Complex | Low |  | R&D | Functional |  |  |  |  | 16 hrs | Checking whether the user is able to log in or not
7 | 7 | Work session | High | OnlineWallet:007 | Adding the money from bank account to the wallet | Satya | Satya | Simple | High |  | R&D | Functional |  |  |  |  | 12 hrs | Checking whether the user is able to add money into the wallet or not
8 | 8 | Work session | High | OnlineWallet:008 | Sending the money to the other wallet account user | Karan | Karan | Complex | High |  | R&D | Functional |  |  |  |  | 18 hrs | Checking whether the user is able to send money to other wallet user or not
9 | 9 | Work session | High | OnlineWallet:009 | Show Balance from user's account | Satya | Satya | Complex | High |  | R&D | Functional |  |  |  |  | 12 hrs | Checking whether the user account balance is shown or not
10 | 10 | Work session | High | OnlineWallet:010 | Admin login | Karan | Karan | Simple | Low |  | R&D | Non-Functional |  |  |  |  | 8 hrs | Checking whether the admin is able to log in or not
11 | 11 | Work session | High | OnlineWallet:011 | Fetching the userlist of active and non-active user | Satya | Satya | Average | High |  | R&D | Non-Functional |  |  |  |  | 12 hrs | Checking whether the application is able to fetch the user list or not
12 | 12 | Work session | Low | OnlineWallet:012 | Changing the user status of user from active to non-active and vice versa | Satya | Satya | Complex | High |  | R&D | Non-Functional |  |  |  |  | 18 hrs | Checking whether the user status can be changed or not
Sprint 2 | Sprint 2
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog (Scrum)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate (in hours) | Adjusted estimate (in hours) | Status | Actual Effort (in hours) | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | OnlineWallet:001 | 1 | Discussion of problem statement & requirements | Satya | 2020-04-30 | 1 | 1 | Completed | 1
|  | 2 | Work allocation among team members | Satya | 2020-04-30 | 1 | 1 | Completed | 1
|  | 3 | ER diagram | Karan | 2020-04-30 | 1 | 1 | Completed | 1
|  | 4 | Sequence diagram | Karan | 2020-04-30 | 4 | 3 | Completed | 2
|  | 5 | Activity diagram | Karan | 2020-04-30 | 4 | 3.5 | Completed | 3
2 | OnlineWallet:002 | 1 | Architecture design | Satya | 2020-05-04 | 2 | 2 | Completed | 2
|  | 2 | Skeleton code design | Satya | 2020-05-04 | 3 | 2 | Completed | 2
|  | 3 | Use case diagram | Karan | 2020-05-04 | 2 | 2 | Completed | 2
|  | 4 | Class diagram | Karan | 2020-05-04 | 4 | 3 | Completed | 3
3 | OnlineWallet:003 | 1 | Creating a Spring boot starter project | Satya | 2020-05-05 | 2 | 1 | Completed | 1
|  | 2 | Adding dependencies in Pom.xml and initializing it | Satya | 2020-05-05 | 1 | 1 | Completed | 1
|  | 3 | Table design | Karan | 2020-05-05 | 2 | 2 | Completed | 2
|  | 4 | Webservice URL Details | Karan | 2020-05-05 | 1 | 1 | Completed | 1
4 | OnlineWallet:004 | 1 | Creation & set up of git repository and pushing of skeleton code into the repository | Satya | 2020-05-06 | 1 | 1 | Completed | 1
|  | 2 | Adding server, jpa properties in application.properties | Karan | 2020-05-06 | 2 | 1 | Completed | 1
5 | OnlineWallet:005 | 1 | Identification of test cases for Account MS | Satya | 2020-05-07 | 2 | 1.5 | Completed | 1
|  | 2 | Creation and submission of test case report anfd UML diagrams sheet | Satya | 2020-05-07 | 2 | 2 | Completed | 1
|  | 3 | Identification of test cases for Transaction MS | Satya | 2020-05-07 | 2 | 1.5 | Completed | 1.5
6 | OnlineWallet:006 | 1 | Entity class design | Satya | 2020-05-08 | 3 | 3 | Completed | 3
|  | 2 | Creating a register method which will take the user data entered from user in frontend | Satya | 2020-05-08 | 3 | 2 | Completed | 2
|  | 3 | Creating a rest controller method to take the details in object form also containig the url with mapping anotation | Satya | 2020-05-08 | 2 | 3 | Completed | 3
|  | 4 | Check tables are populated in DB | Karan | 2020-05-08 | 3 | 2 | Completed | 1
|  | 5 | Populate the Data | Karan | 2020-05-08 | 3 | 3 | Completed | 3
7 | OnlineWallet:007 | 1 | For register method - creating a service method to check whether the data is correct or not otherise throw exception | Satya | 2020-05-09 | 3 | 4 | Completed | 3
|  | 2 | For register method- creating a dao method which will contain the entitymanager which persists the data in database | Satya | 2020-05-09 | 3 | 4 | Completed | 3
|  | 3 | Login method which will conduct the login criteria by taking data from user | Karan | 2020-05-09 | 5 | 5 | Completed | 5
|  | 4 | Creating rest controller method to take the details and also containig the url with mapping anotation | Karan | 2020-05-09 | 2 | 2 | Completed | 2
|  | 5 | Creating service method to check whether the data is correct or not by comparing it from database otherise throw exception | Karan | 2020-05-09 | 3 | 3 | Completed | 3
|  | 6 | Creating dao method which contains the entitymanager which will take help from jpql for verification | Karan | 2020-05-09 | 2 | 2 | Completed | 2
8 | Online Wallet:008 | 1 | Creating add money method which will enable users to add money to their wallet | Satya | 2020-05-10 | 4 | 4 | Completed | 4
|  | 2 | Creating rest controller method to link the work of service with help of anotations | Satya | 2020-05-10 | 3 | 3 | Completed | 3
|  | 3 | Creating service method which calls to dao method fetching the user and saving the new updated incremented balance | Satya | 2020-05-10 | 3 | 3 | Completed | 3
|  | 4 | Creating send money method which will help users to transfer funds from one wallet account to another | Karan | 2020-05-10 | 3 | 1.5 | Completed | 2
|  | 5 | Creating rest controller method to take the details and also containing the url with mapping anotation | Karan | 2020-05-10 | 2 | 2 | Completed | 2
|  | 6 | Creating service method to check whether the data is correct or not by comparing it from database otherise throw exception | Karan | 2020-05-10 | 2 | 2.5 | Completed | 2
|  | 7 | Creating dao method which contains the entitymanager which will take help from jpa query to take the list of the users | Karan | 2020-05-10 | 1 | 1.5 | Completed | 2
9 | Online Wallet:008 | 1 | Creating show balance method which helps users to check the balance in their wallet account. | Satya | 2020-05-11 | 2 | 1.5 | Completed | 2
|  | 2 | Creating rest controller method to take the details and also contains the url with mapping anotation | Satya | 2020-05-11 | 2 | 2 | Completed | 2
|  | 3 | Creating service method to check whether the data is correct or not by comparing it from database otherise throw exception | Satya | 2020-05-11 | 2 | 1 | Completed | 1
|  | 4 | Creating dao method which contains the entitymanager which will take help from jpa query to take the list of the users | Satya | 2020-05-11 | 1 | 1 | Completed | 1
|  | 5 | Creating userlist method which will show the email list of the users based on their status | Satya | 2020-05-11 | 2 | 2 | Completed | 2
|  | 6 | Creating rest controller method to take the details and also containig the url with mapping anotation | Satya | 2020-05-11 | 2 | 1 | Completed | 1
|  | 7 | Creating service method to check whether the data is correct or not by comparing it from database otherise throw exception | Satya | 2020-05-11 | 2 | 2 | Completed | 2
|  | 8 | Creating dao method which contains the entitymanager which will take help from jpa query to return the list of the users | Satya | 2020-05-11 | 2 | 3 | Completed | 2.5
|  | 9 | Creating AdminLogin method which will take the Admin data entered from user in frontend | Karan | 2020-05-11 | 3 | 1.5 | Completed | 2
|  | 10 | Creating rest controller method to take the details also containig the url with mapping anotation | Karan | 2020-05-11 | 2 | 2 | Completed | 2
|  | 11 | Ceating service method check the data wheather it is correct or not otherise throw exception | Karan | 2020-05-11 | 2 | 1.5 | Completed | 1.5
|  | 12 | Creating dao method contains the entitymanager which will take help from jpql for verification | Karan | 2020-05-11 | 1 | 1.5 | Completed | 1.5
10 | OnlineWallet: 009 | 1 | Creating changestatus method which will change the user's status to active or non active | Satya | 2020-05-12 | 3 | 2 | Completed | 2
|  | 2 | Creating rest controller method to take the details and also containig the url with mapping anotation | Satya | 2020-05-12 | 2 | 2 | Completed | 2
|  | 3 | Creating service method to check whether the data is correct or not by comparing it from database otherise throw exception | Satya | 2020-05-12 | 2 | 2 | Completed | 2
|  | 4 | Creating dao method which contains entitymanager method to fetch the users | Satya | 2020-05-12 | 3 | 2 | Completed | 2
|  | 5 | Testing the code for Account MS using postman | Satya | 2020-05-12 | 2 | 2 | Completed | 2
|  | 6 | Testing the code for Transaction MS using postman | Karan | 2020-05-12 | 2 | 2 | Completed | 2
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.